## Data
task_id | task_name | assignee | department | assigned_date | due_date | completion_date | status | priority | is_overdue | days_overdue | sprint
TASK0001 | Budget Review | Bob Martinez | HR | 2025-11-10 | 2025-11-18 |  | Overdue | Medium | TRUE | 2 | 8
TASK0002 | Product Launch | Henry Davis | IT | 2025-02-27 | 2025-03-24 |  | Overdue | Medium | TRUE | 9 | 10
TASK0003 | Process Improvement | Henry Davis | IT | 2026-01-06 | 2026-01-23 |  | In Progress | Low | FALSE | 0 | 4
TASK0004 | Budget Review | Grace Chen | HR | 2026-01-22 | 2026-02-16 |  | In Progress | High | FALSE | 0 | 9
TASK0005 | Budget Review | Emma Brown | Sales | 2026-03-13 | 2026-03-28 | 2026-04-03 | Completed | Medium | TRUE | 6 | 7
TASK0006 | Risk Assessment | Karen Thomas | Finance | 2025-01-20 | 2025-02-06 | 2025-02-05 | Completed | High | FALSE | 0 | 8
TASK0007 | Process Improvement | Liam Jackson | HR | 2025-05-27 | 2025-06-23 |  | Cancelled | Medium | FALSE | 0 | 7
TASK0008 | System Upgrade | Frank Wilson | Finance | 2025-11-05 | 2025-11-20 | 2025-11-21 | Completed | Medium | TRUE | 1 | 5
TASK0009 | Policy Update | David Lee | Operations | 2025-10-11 | 2025-11-01 | 2025-10-30 | Completed | Medium | FALSE | 0 | 2
TASK0010 | Performance Review | Emma Brown | Sales | 2026-02-09 | 2026-02-19 |  | Overdue | Low | TRUE | 5 | 9
TASK0011 | Quarterly Report | Karen Thomas | Finance | 2025-12-25 | 2026-01-18 | 2026-01-23 | Completed | High | TRUE | 5 | 9
TASK0012 | Risk Assessment | James Anderson | Sales | 2025-08-16 | 2025-09-03 |  | Overdue | Medium | TRUE | 1 | 6
TASK0013 | Risk Assessment | Carol White | IT | 2026-01-20 | 2026-02-07 |  | In Progress | High | FALSE | 0 | 7
TASK0014 | Budget Review | Bob Martinez | HR | 2025-09-09 | 2025-10-03 |  | In Progress | Medium | FALSE | 0 | 8
TASK0015 | Client Presentation | Emma Brown | Sales | 2025-05-05 | 2025-05-19 | 2025-05-26 | Completed | Critical | TRUE | 7 | 10
TASK0016 | Data Migration | Maria Harris | IT | 2026-02-17 | 2026-02-27 | 2026-03-01 | Completed | High | TRUE | 2 | 9
TASK0017 | Vendor Evaluation | James Anderson | Sales | 2025-07-04 | 2025-07-17 |  | Overdue | Medium | TRUE | 8 | 10
TASK0018 | Budget Review | Maria Harris | IT | 2025-12-14 | 2026-01-05 | 2026-01-09 | Completed | High | TRUE | 4 | 2
TASK0019 | Team Meeting | Grace Chen | HR | 2025-08-12 | 2025-09-02 | 2025-09-04 | Completed | High | TRUE | 2 | 10
TASK0020 | Contract Negotiation | Grace Chen | HR | 2025-10-01 | 2025-10-13 | 2025-10-20 | Completed | High | TRUE | 7 | 7
TASK0021 | Code Review | Bob Martinez | HR | 2025-08-11 | 2025-09-01 |  | Cancelled | High | FALSE | 0 | 4
TASK0022 | Data Migration | Grace Chen | HR | 2025-11-19 | 2025-12-13 |  | Overdue | Low | TRUE | 9 | 3
TASK0023 | System Upgrade | Liam Jackson | HR | 2025-07-25 | 2025-08-16 |  | Cancelled | Critical | FALSE | 0 | 3
TASK0024 | Team Meeting | David Lee | Operations | 2025-07-28 | 2025-08-23 |  | In Progress | High | FALSE | 0 | 6
TASK0025 | Compliance Audit | Alice Johnson | Finance | 2025-10-10 | 2025-10-16 | 2025-10-19 | Completed | Medium | TRUE | 3 | 8
TASK0026 | Dashboard Setup | Bob Martinez | HR | 2025-01-19 | 2025-01-26 | 2025-01-28 | Completed | Critical | TRUE | 2 | 7
TASK0027 | Team Meeting | Carol White | IT | 2025-09-22 | 2025-10-16 | 2025-10-15 | Completed | High | FALSE | 0 | 4
TASK0028 | Contract Negotiation | Emma Brown | Sales | 2025-09-23 | 2025-10-03 | 2025-10-01 | Completed | Medium | FALSE | 0 | 10
TASK0029 | Budget Review | Carol White | IT | 2025-02-07 | 2025-02-17 |  | Overdue | Medium | TRUE | 10 | 10
TASK0030 | Product Launch | Karen Thomas | Finance | 2025-08-02 | 2025-08-26 |  | In Progress | Low | FALSE | 0 | 5
TASK0031 | Process Improvement | Emma Brown | Sales | 2025-05-09 | 2025-05-12 | 2025-05-13 | Completed | High | TRUE | 1 | 9
TASK0032 | Training Session | Maria Harris | IT | 2025-05-23 | 2025-05-28 | 2025-06-01 | Completed | Low | TRUE | 4 | 4
TASK0033 | Security Patch | Karen Thomas | Finance | 2026-02-27 | 2026-03-22 |  | In Progress | High | FALSE | 0 | 8
TASK0034 | Client Presentation | Emma Brown | Sales | 2025-01-17 | 2025-01-23 | 2025-01-26 | Completed | Low | TRUE | 3 | 2
TASK0035 | Market Analysis | Isabella Taylor | Operations | 2025-05-23 | 2025-05-31 |  | Overdue | Low | TRUE | 19 | 4
TASK0036 | Market Analysis | James Anderson | Sales | 2026-02-26 | 2026-03-05 | 2026-03-04 | Completed | Medium | FALSE | 0 | 3
TASK0037 | Team Meeting | Henry Davis | IT | 2026-02-06 | 2026-02-11 |  | Cancelled | Medium | FALSE | 0 | 1
TASK0038 | Product Launch | Liam Jackson | HR | 2025-07-31 | 2025-08-11 |  | Overdue | Low | TRUE | 1 | 2
TASK0039 | Budget Review | Liam Jackson | HR | 2025-11-28 | 2025-12-21 | 2025-12-22 | Completed | Medium | TRUE | 1 | 9
TASK0040 | System Upgrade | David Lee | Operations | 2025-01-31 | 2025-02-25 | 2025-03-03 | Completed | Low | TRUE | 6 | 1
TASK0041 | Stakeholder Report | Carol White | IT | 2025-01-21 | 2025-01-29 |  | In Progress | High | FALSE | 0 | 8
TASK0042 | Risk Assessment | Emma Brown | Sales | 2025-08-14 | 2025-08-28 |  | Cancelled | Medium | FALSE | 0 | 4
TASK0043 | System Upgrade | Carol White | IT | 2025-01-09 | 2025-01-30 | 2025-02-06 | Completed | Critical | TRUE | 7 | 3
TASK0044 | Training Session | Bob Martinez | HR | 2025-07-07 | 2025-07-15 |  | In Progress | Medium | FALSE | 0 | 8
TASK0045 | Policy Update | Maria Harris | IT | 2025-02-28 | 2025-03-14 |  | Overdue | Medium | TRUE | 3 | 9
TASK0046 | System Upgrade | Isabella Taylor | Operations | 2025-08-08 | 2025-08-24 | 2025-08-28 | Completed | High | TRUE | 4 | 10
TASK0047 | Risk Assessment | Emma Brown | Sales | 2025-01-12 | 2025-01-31 |  | Cancelled | High | FALSE | 0 | 10
TASK0048 | System Upgrade | Isabella Taylor | Operations | 2025-12-03 | 2025-12-17 | 2025-12-15 | Completed | Medium | FALSE | 0 | 8
TASK0049 | Policy Update | Olivia Lewis | Sales | 2025-07-14 | 2025-07-29 |  | Cancelled | Medium | FALSE | 0 | 8
TASK0050 | Data Migration | James Anderson | Sales | 2026-01-09 | 2026-01-18 | 2026-01-23 | Completed | Critical | TRUE | 5 | 8
TASK0051 | Code Review | Grace Chen | HR | 2026-01-26 | 2026-02-18 |  | In Progress | Medium | FALSE | 0 | 3
TASK0052 | Process Improvement | James Anderson | Sales | 2025-02-21 | 2025-03-13 | 2025-03-20 | Completed | Medium | TRUE | 7 | 10
TASK0053 | Client Presentation | Nathan Clark | Operations | 2026-03-24 | 2026-04-16 | 2026-04-22 | Completed | Medium | TRUE | 6 | 3
TASK0054 | Training Session | Maria Harris | IT | 2025-06-11 | 2025-06-17 | 2025-06-16 | Completed | High | FALSE | 0 | 5
TASK0055 | Code Review | Maria Harris | IT | 2025-09-27 | 2025-10-04 | 2025-10-03 | Completed | High | FALSE | 0 | 10
TASK0056 | Quarterly Report | Emma Brown | Sales | 2025-11-16 | 2025-11-20 | 2025-11-19 | Completed | High | FALSE | 0 | 6
TASK0057 | Vendor Evaluation | Carol White | IT | 2025-12-28 | 2026-01-10 |  | In Progress | Critical | FALSE | 0 | 6
TASK0058 | Dashboard Setup | Maria Harris | IT | 2026-01-19 | 2026-02-05 |  | Overdue | Medium | TRUE | 1 | 4
TASK0059 | Contract Negotiation | Henry Davis | IT | 2025-09-15 | 2025-10-13 | 2025-10-15 | Completed | High | TRUE | 2 | 2
TASK0060 | Stakeholder Report | Emma Brown | Sales | 2025-02-15 | 2025-02-20 | 2025-02-26 | Completed | High | TRUE | 6 | 1
TASK0061 | Policy Update | Bob Martinez | HR | 2026-01-15 | 2026-02-08 | 2026-02-15 | Completed | Low | TRUE | 7 | 1
TASK0062 | Contract Negotiation | David Lee | Operations | 2025-10-17 | 2025-11-05 |  | Overdue | Low | TRUE | 15 | 10
TASK0063 | Market Analysis | Liam Jackson | HR | 2026-01-21 | 2026-02-15 | 2026-02-17 | Completed | Medium | TRUE | 2 | 2
TASK0064 | Budget Review | Liam Jackson | HR | 2025-03-04 | 2025-03-18 | 2025-03-20 | Completed | Medium | TRUE | 2 | 4
TASK0065 | Product Launch | Carol White | IT | 2025-06-14 | 2025-07-06 | 2025-07-07 | Completed | High | TRUE | 1 | 5
TASK0066 | Dashboard Setup | Grace Chen | HR | 2026-03-03 | 2026-03-24 | 2026-03-31 | Completed | Medium | TRUE | 7 | 4
TASK0067 | Market Analysis | Maria Harris | IT | 2026-01-17 | 2026-02-02 | 2026-02-06 | Completed | High | TRUE | 4 | 5
TASK0068 | Budget Review | David Lee | Operations | 2025-05-10 | 2025-05-17 |  | In Progress | Medium | FALSE | 0 | 9
TASK0069 | Stakeholder Report | Liam Jackson | HR | 2026-02-18 | 2026-02-24 |  | In Progress | High | FALSE | 0 | 6
TASK0070 | Training Session | Olivia Lewis | Sales | 2025-02-08 | 2025-02-25 |  | In Progress | Critical | FALSE | 0 | 7
TASK0071 | Policy Update | Olivia Lewis | Sales | 2025-07-03 | 2025-07-22 |  | Cancelled | High | FALSE | 0 | 2
TASK0072 | Budget Review | Grace Chen | HR | 2025-04-25 | 2025-05-17 |  | Cancelled | Medium | FALSE | 0 | 8
TASK0073 | Team Meeting | Isabella Taylor | Operations | 2025-02-28 | 2025-03-18 |  | In Progress | Critical | FALSE | 0 | 2
TASK0074 | Security Patch | Alice Johnson | Finance | 2025-12-10 | 2026-01-06 | 2026-01-11 | Completed | Medium | TRUE | 5 | 6
TASK0075 | Policy Update | Henry Davis | IT | 2025-02-23 | 2025-03-19 |  | Cancelled | Medium | FALSE | 0 | 5
TASK0076 | Process Improvement | Bob Martinez | HR | 2026-02-19 | 2026-03-14 |  | In Progress | Critical | FALSE | 0 | 8
TASK0077 | Policy Update | David Lee | Operations | 2025-12-10 | 2025-12-30 |  | Overdue | High | TRUE | 6 | 7
TASK0078 | Market Analysis | Liam Jackson | HR | 2025-03-08 | 2025-03-13 | 2025-03-20 | Completed | High | TRUE | 7 | 4
TASK0079 | Team Meeting | Isabella Taylor | Operations | 2025-09-06 | 2025-10-04 |  | In Progress | High | FALSE | 0 | 5
TASK0080 | Performance Review | Olivia Lewis | Sales | 2025-10-21 | 2025-11-19 | 2025-11-17 | Completed | Medium | FALSE | 0 | 2
TASK0081 | Stakeholder Report | Karen Thomas | Finance | 2026-01-31 | 2026-02-20 | 2026-02-19 | Completed | Low | FALSE | 0 | 3
TASK0082 | Quarterly Report | Bob Martinez | HR | 2025-02-13 | 2025-02-28 |  | In Progress | Medium | FALSE | 0 | 6
TASK0083 | Compliance Audit | Karen Thomas | Finance | 2025-07-19 | 2025-07-22 | 2025-07-23 | Completed | High | TRUE | 1 | 9
TASK0084 | Performance Review | Henry Davis | IT | 2026-03-25 | 2026-03-29 | 2026-04-04 | Completed | Medium | TRUE | 6 | 10
TASK0085 | Vendor Evaluation | Karen Thomas | Finance | 2026-03-26 | 2026-03-29 | 2026-04-02 | Completed | Low | TRUE | 4 | 3
TASK0086 | Stakeholder Report | Carol White | IT | 2025-01-14 | 2025-01-23 |  | Overdue | Critical | TRUE | 5 | 7
TASK0087 | Quarterly Report | Grace Chen | HR | 2026-02-14 | 2026-02-24 | 2026-02-28 | Completed | Medium | TRUE | 4 | 2
TASK0088 | Policy Update | Nathan Clark | Operations | 2025-09-30 | 2025-10-29 | 2025-11-04 | Completed | Critical | TRUE | 6 | 1
TASK0089 | Vendor Evaluation | Olivia Lewis | Sales | 2025-12-27 | 2026-01-25 | 2026-02-01 | Completed | Low | TRUE | 7 | 3
TASK0090 | Process Improvement | Bob Martinez | HR | 2025-01-19 | 2025-02-03 |  | Overdue | Medium | TRUE | 4 | 8
TASK0091 | Product Launch | Bob Martinez | HR | 2025-10-11 | 2025-10-16 |  | Overdue | Medium | TRUE | 17 | 2
TASK0092 | Quarterly Report | Grace Chen | HR | 2025-05-02 | 2025-05-07 | 2025-05-12 | Completed | Medium | TRUE | 5 | 2
TASK0093 | Budget Review | Henry Davis | IT | 2025-10-05 | 2025-10-08 | 2025-10-06 | Completed | Medium | FALSE | 0 | 10
TASK0094 | Performance Review | David Lee | Operations | 2025-02-11 | 2025-03-06 | 2025-03-05 | Completed | Medium | FALSE | 0 | 9
TASK0095 | Data Migration | Frank Wilson | Finance | 2025-10-14 | 2025-11-09 |  | Overdue | Medium | TRUE | 11 | 10
TASK0096 | Process Improvement | Grace Chen | HR | 2025-09-18 | 2025-10-05 | 2025-10-09 | Completed | Low | TRUE | 4 | 2
TASK0097 | Risk Assessment | David Lee | Operations | 2025-08-17 | 2025-09-07 | 2025-09-09 | Completed | Low | TRUE | 2 | 7
TASK0098 | Code Review | Nathan Clark | Operations | 2025-05-06 | 2025-05-11 | 2025-05-12 | Completed | High | TRUE | 1 | 5
TASK0099 | Market Analysis | James Anderson | Sales | 2025-07-05 | 2025-07-12 |  | In Progress | Medium | FALSE | 0 | 5
TASK0100 | Compliance Audit | Grace Chen | HR | 2026-02-19 | 2026-02-22 |  | In Progress | High | FALSE | 0 | 7
TASK0101 | Budget Review | Emma Brown | Sales | 2025-09-15 | 2025-09-27 | 2025-09-30 | Completed | Medium | TRUE | 3 | 5
TASK0102 | Contract Negotiation | Isabella Taylor | Operations | 2025-05-23 | 2025-06-01 |  | In Progress | Medium | FALSE | 0 | 8
TASK0103 | Contract Negotiation | Liam Jackson | HR | 2025-08-25 | 2025-09-06 | 2025-09-13 | Completed | Medium | TRUE | 7 | 6
TASK0104 | Code Review | Henry Davis | IT | 2026-01-18 | 2026-02-03 |  | Overdue | Medium | TRUE | 14 | 2
TASK0105 | Policy Update | Henry Davis | IT | 2025-06-22 | 2025-07-08 | 2025-07-06 | Completed | Medium | FALSE | 0 | 6
TASK0106 | Budget Review | Bob Martinez | HR | 2025-02-04 | 2025-02-14 |  | Overdue | Critical | TRUE | 11 | 9
TASK0107 | Security Patch | Frank Wilson | Finance | 2026-02-11 | 2026-02-14 | 2026-02-16 | Completed | High | TRUE | 2 | 1
TASK0108 | Team Meeting | Maria Harris | IT | 2025-04-18 | 2025-05-07 | 2025-05-11 | Completed | Low | TRUE | 4 | 8
TASK0109 | Market Analysis | Bob Martinez | HR | 2025-07-22 | 2025-08-14 |  | Cancelled | High | FALSE | 0 | 1
TASK0110 | Dashboard Setup | Grace Chen | HR | 2025-06-24 | 2025-07-21 |  | In Progress | Medium | FALSE | 0 | 4
TASK0111 | Product Launch | James Anderson | Sales | 2025-07-30 | 2025-08-06 | 2025-08-11 | Completed | Critical | TRUE | 5 | 8
TASK0112 | Training Session | Carol White | IT | 2025-04-01 | 2025-04-26 |  | Cancelled | Low | FALSE | 0 | 10
TASK0113 | Policy Update | Maria Harris | IT | 2025-06-26 | 2025-07-07 | 2025-07-05 | Completed | High | FALSE | 0 | 10
TASK0114 | Code Review | Maria Harris | IT | 2025-03-09 | 2025-03-20 | 2025-03-19 | Completed | Medium | FALSE | 0 | 8
TASK0115 | Team Meeting | David Lee | Operations | 2025-05-12 | 2025-05-20 | 2025-05-22 | Completed | Critical | TRUE | 2 | 10
TASK0116 | Data Migration | Olivia Lewis | Sales | 2025-04-20 | 2025-05-15 | 2025-05-21 | Completed | Medium | TRUE | 6 | 6
TASK0117 | Dashboard Setup | Maria Harris | IT | 2025-12-10 | 2025-12-29 |  | In Progress | Medium | FALSE | 0 | 7
TASK0118 | Compliance Audit | Alice Johnson | Finance | 2026-02-24 | 2026-03-21 | 2026-03-22 | Completed | High | TRUE | 1 | 9
TASK0119 | Product Launch | Henry Davis | IT | 2025-07-13 | 2025-08-09 |  | Overdue | Medium | TRUE | 6 | 4
TASK0120 | Risk Assessment | Isabella Taylor | Operations | 2026-01-17 | 2026-02-03 | 2026-02-06 | Completed | Low | TRUE | 3 | 6
TASK0121 | Contract Negotiation | Bob Martinez | HR | 2025-06-26 | 2025-07-03 |  | Cancelled | High | FALSE | 0 | 7
TASK0122 | Contract Negotiation | Alice Johnson | Finance | 2026-02-22 | 2026-03-15 | 2026-03-17 | Completed | High | TRUE | 2 | 4
TASK0123 | Process Improvement | Grace Chen | HR | 2025-05-06 | 2025-05-13 | 2025-05-18 | Completed | Medium | TRUE | 5 | 4
TASK0124 | Stakeholder Report | Henry Davis | IT | 2025-08-03 | 2025-09-01 |  | In Progress | Low | FALSE | 0 | 7
TASK0125 | Market Analysis | Liam Jackson | HR | 2025-10-08 | 2025-11-01 |  | In Progress | Low | FALSE | 0 | 3
TASK0126 | Policy Update | Grace Chen | HR | 2025-07-18 | 2025-08-07 |  | Overdue | High | TRUE | 11 | 9
TASK0127 | Team Meeting | Olivia Lewis | Sales | 2025-05-10 | 2025-06-04 |  | Cancelled | Low | FALSE | 0 | 7
TASK0128 | System Upgrade | Liam Jackson | HR | 2025-05-14 | 2025-05-18 | 2025-05-21 | Completed | Medium | TRUE | 3 | 1
TASK0129 | Risk Assessment | Liam Jackson | HR | 2025-05-27 | 2025-06-25 |  | Cancelled | Medium | FALSE | 0 | 9
TASK0130 | Client Presentation | David Lee | Operations | 2025-09-07 | 2025-09-24 | 2025-09-30 | Completed | Medium | TRUE | 6 | 5
TASK0131 | Budget Review | David Lee | Operations | 2025-06-17 | 2025-07-15 | 2025-07-13 | Completed | Low | FALSE | 0 | 10
TASK0132 | Vendor Evaluation | Frank Wilson | Finance | 2025-12-15 | 2025-12-18 |  | In Progress | Medium | FALSE | 0 | 2
TASK0133 | Quarterly Report | Maria Harris | IT | 2026-02-13 | 2026-02-22 |  | Overdue | Medium | TRUE | 2 | 4
TASK0134 | Product Launch | James Anderson | Sales | 2025-04-29 | 2025-05-20 | 2025-05-23 | Completed | Low | TRUE | 3 | 10
TASK0135 | Vendor Evaluation | Alice Johnson | Finance | 2025-04-25 | 2025-05-04 |  | Overdue | Medium | TRUE | 8 | 7
TASK0136 | Data Migration | Maria Harris | IT | 2025-11-16 | 2025-12-04 |  | Overdue | High | TRUE | 9 | 10
TASK0137 | Team Meeting | Frank Wilson | Finance | 2025-11-02 | 2025-11-07 |  | Overdue | High | TRUE | 13 | 9
TASK0138 | Market Analysis | Frank Wilson | Finance | 2025-10-15 | 2025-10-26 |  | Overdue | Medium | TRUE | 15 | 6
TASK0139 | Market Analysis | Grace Chen | HR | 2026-01-21 | 2026-02-11 |  | In Progress | High | FALSE | 0 | 2
TASK0140 | Client Presentation | Liam Jackson | HR | 2025-08-12 | 2025-08-24 |  | Cancelled | High | FALSE | 0 | 6
TASK0141 | Client Presentation | Carol White | IT | 2025-09-07 | 2025-09-10 | 2025-09-11 | Completed | High | TRUE | 1 | 4
TASK0142 | Process Improvement | Grace Chen | HR | 2026-02-04 | 2026-03-04 | 2026-03-11 | Completed | Medium | TRUE | 7 | 5
TASK0143 | Stakeholder Report | Liam Jackson | HR | 2025-06-23 | 2025-07-02 | 2025-07-05 | Completed | Medium | TRUE | 3 | 4
TASK0144 | Security Patch | Emma Brown | Sales | 2025-04-08 | 2025-04-26 | 2025-04-30 | Completed | Low | TRUE | 4 | 10
TASK0145 | Compliance Audit | James Anderson | Sales | 2025-03-21 | 2025-03-28 | 2025-03-29 | Completed | High | TRUE | 1 | 3
TASK0146 | Dashboard Setup | Nathan Clark | Operations | 2025-09-21 | 2025-10-15 |  | In Progress | High | FALSE | 0 | 3
TASK0147 | Training Session | James Anderson | Sales | 2025-10-31 | 2025-11-09 |  | Cancelled | Medium | FALSE | 0 | 5
TASK0148 | Team Meeting | Maria Harris | IT | 2025-03-19 | 2025-04-06 |  | Overdue | Low | TRUE | 7 | 5
TASK0149 | Product Launch | Bob Martinez | HR | 2026-02-25 | 2026-03-11 |  | Cancelled | Medium | FALSE | 0 | 8
TASK0150 | Data Migration | Carol White | IT | 2025-01-19 | 2025-01-23 | 2025-01-23 | Completed | Low | FALSE | 0 | 1
TASK0151 | Dashboard Setup | Isabella Taylor | Operations | 2025-05-21 | 2025-05-25 | 2025-05-23 | Completed | Medium | FALSE | 0 | 1
TASK0152 | Stakeholder Report | Maria Harris | IT | 2025-11-11 | 2025-11-26 | 2025-11-26 | Completed | High | FALSE | 0 | 2
TASK0153 | Team Meeting | Olivia Lewis | Sales | 2025-01-01 | 2025-01-11 | 2025-01-10 | Completed | High | FALSE | 0 | 4
TASK0154 | Data Migration | Grace Chen | HR | 2025-08-09 | 2025-08-12 | 2025-08-13 | Completed | Critical | TRUE | 1 | 9
TASK0155 | Product Launch | Grace Chen | HR | 2025-04-28 | 2025-05-07 |  | Overdue | Medium | TRUE | 7 | 5
TASK0156 | Compliance Audit | Isabella Taylor | Operations | 2025-04-13 | 2025-05-06 |  | In Progress | Medium | FALSE | 0 | 3
TASK0157 | Risk Assessment | Emma Brown | Sales | 2026-01-24 | 2026-02-15 | 2026-02-14 | Completed | Low | FALSE | 0 | 5
TASK0158 | Code Review | Carol White | IT | 2025-02-10 | 2025-02-13 | 2025-02-20 | Completed | Critical | TRUE | 7 | 1
TASK0159 | Contract Negotiation | Carol White | IT | 2025-08-02 | 2025-08-11 | 2025-08-09 | Completed | Critical | FALSE | 0 | 8
TASK0160 | Quarterly Report | Isabella Taylor | Operations | 2025-05-07 | 2025-06-02 |  | Overdue | Medium | TRUE | 11 | 5
TASK0161 | Stakeholder Report | James Anderson | Sales | 2025-05-12 | 2025-05-21 |  | Overdue | High | TRUE | 5 | 10
TASK0162 | Market Analysis | Nathan Clark | Operations | 2025-02-05 | 2025-02-17 |  | In Progress | Medium | FALSE | 0 | 10
TASK0163 | System Upgrade | Liam Jackson | HR | 2025-09-28 | 2025-10-09 |  | Overdue | High | TRUE | 5 | 9
TASK0164 | Stakeholder Report | Henry Davis | IT | 2025-01-14 | 2025-02-05 | 2025-02-06 | Completed | High | TRUE | 1 | 5
TASK0165 | Policy Update | Frank Wilson | Finance | 2025-11-15 | 2025-11-26 |  | In Progress | High | FALSE | 0 | 1
TASK0166 | Training Session | Liam Jackson | HR | 2025-04-17 | 2025-04-23 |  | Overdue | High | TRUE | 15 | 2
TASK0167 | Product Launch | Carol White | IT | 2025-02-24 | 2025-03-25 | 2025-03-25 | Completed | Medium | FALSE | 0 | 8
TASK0168 | Training Session | Alice Johnson | Finance | 2025-06-24 | 2025-06-30 |  | Cancelled | Critical | FALSE | 0 | 6
TASK0169 | Team Meeting | Isabella Taylor | Operations | 2025-10-07 | 2025-10-14 | 2025-10-14 | Completed | Low | FALSE | 0 | 9
TASK0170 | Compliance Audit | Karen Thomas | Finance | 2025-10-26 | 2025-11-24 | 2025-11-30 | Completed | Medium | TRUE | 6 | 1
TASK0171 | Policy Update | Carol White | IT | 2026-01-29 | 2026-02-23 | 2026-02-23 | Completed | Medium | FALSE | 0 | 1
TASK0172 | Dashboard Setup | James Anderson | Sales | 2025-11-01 | 2025-11-18 | 2025-11-23 | Completed | Medium | TRUE | 5 | 7
TASK0173 | System Upgrade | Liam Jackson | HR | 2025-07-08 | 2025-08-04 |  | Cancelled | Medium | FALSE | 0 | 6
TASK0174 | Product Launch | Henry Davis | IT | 2025-07-12 | 2025-07-26 |  | Overdue | Critical | TRUE | 18 | 4
TASK0175 | Vendor Evaluation | Bob Martinez | HR | 2025-07-30 | 2025-08-06 | 2025-08-07 | Completed | Low | TRUE | 1 | 2
TASK0176 | Stakeholder Report | Olivia Lewis | Sales | 2026-03-19 | 2026-04-15 | 2026-04-15 | Completed | High | FALSE | 0 | 10
TASK0177 | Stakeholder Report | David Lee | Operations | 2025-10-18 | 2025-10-31 |  | Overdue | Medium | TRUE | 8 | 7
TASK0178 | Dashboard Setup | Henry Davis | IT | 2026-03-04 | 2026-03-22 |  | Overdue | Medium | TRUE | 9 | 6
TASK0179 | Dashboard Setup | Bob Martinez | HR | 2025-08-15 | 2025-08-20 |  | Overdue | Low | TRUE | 1 | 9
TASK0180 | Market Analysis | David Lee | Operations | 2026-03-21 | 2026-04-03 | 2026-04-09 | Completed | Medium | TRUE | 6 | 3
TASK0181 | Compliance Audit | Karen Thomas | Finance | 2025-06-06 | 2025-06-25 | 2025-06-28 | Completed | Low | TRUE | 3 | 7
TASK0182 | Code Review | Isabella Taylor | Operations | 2025-08-15 | 2025-08-30 |  | In Progress | Medium | FALSE | 0 | 6
TASK0183 | Dashboard Setup | Bob Martinez | HR | 2025-02-28 | 2025-03-11 | 2025-03-10 | Completed | High | FALSE | 0 | 2
TASK0184 | Security Patch | Emma Brown | Sales | 2025-04-20 | 2025-04-28 |  | Cancelled | High | FALSE | 0 | 7
TASK0185 | Data Migration | Bob Martinez | HR | 2025-08-04 | 2025-08-12 |  | Overdue | Medium | TRUE | 19 | 4
TASK0186 | Data Migration | Carol White | IT | 2025-02-27 | 2025-03-03 | 2025-03-01 | Completed | Medium | FALSE | 0 | 5
TASK0187 | Risk Assessment | Henry Davis | IT | 2026-02-02 | 2026-02-07 |  | In Progress | Low | FALSE | 0 | 7
TASK0188 | Compliance Audit | David Lee | Operations | 2026-01-30 | 2026-02-22 |  | Overdue | High | TRUE | 18 | 3
TASK0189 | Training Session | Bob Martinez | HR | 2025-02-02 | 2025-02-16 |  | Cancelled | Low | FALSE | 0 | 10
TASK0190 | Budget Review | Carol White | IT | 2026-01-03 | 2026-01-28 |  | In Progress | High | FALSE | 0 | 5
TASK0191 | Budget Review | Liam Jackson | HR | 2025-04-24 | 2025-05-09 | 2025-05-08 | Completed | Medium | FALSE | 0 | 7
TASK0192 | Security Patch | Bob Martinez | HR | 2025-05-14 | 2025-06-08 |  | Overdue | Medium | TRUE | 8 | 9
TASK0193 | Quarterly Report | Maria Harris | IT | 2025-04-04 | 2025-04-23 |  | Overdue | Medium | TRUE | 18 | 5
TASK0194 | Performance Review | Grace Chen | HR | 2025-04-30 | 2025-05-07 | 2025-05-13 | Completed | Low | TRUE | 6 | 2
TASK0195 | Team Meeting | James Anderson | Sales | 2025-04-21 | 2025-05-17 | 2025-05-22 | Completed | Medium | TRUE | 5 | 2
TASK0196 | Product Launch | Carol White | IT | 2025-08-27 | 2025-09-18 | 2025-09-18 | Completed | Low | FALSE | 0 | 9
TASK0197 | Budget Review | Emma Brown | Sales | 2026-02-04 | 2026-02-07 |  | Cancelled | High | FALSE | 0 | 3
TASK0198 | Product Launch | Liam Jackson | HR | 2025-06-26 | 2025-07-13 | 2025-07-19 | Completed | Medium | TRUE | 6 | 5
TASK0199 | Market Analysis | Grace Chen | HR | 2025-02-10 | 2025-02-26 | 2025-03-04 | Completed | High | TRUE | 6 | 2
TASK0200 | Client Presentation | Olivia Lewis | Sales | 2025-03-15 | 2025-03-24 |  | In Progress | High | FALSE | 0 | 10
TASK0201 | Quarterly Report | Nathan Clark | Operations | 2025-05-25 | 2025-06-21 |  | Cancelled | High | FALSE | 0 | 1
TASK0202 | Product Launch | James Anderson | Sales | 2025-10-25 | 2025-11-02 | 2025-11-08 | Completed | Medium | TRUE | 6 | 6
TASK0203 | Risk Assessment | Olivia Lewis | Sales | 2026-01-13 | 2026-01-20 |  | Overdue | Low | TRUE | 16 | 4
TASK0204 | Compliance Audit | Nathan Clark | Operations | 2025-01-26 | 2025-02-19 | 2025-02-23 | Completed | High | TRUE | 4 | 10
TASK0205 | Client Presentation | James Anderson | Sales | 2025-04-05 | 2025-05-02 |  | Overdue | Medium | TRUE | 11 | 9
TASK0206 | Market Analysis | Grace Chen | HR | 2025-05-07 | 2025-05-17 | 2025-05-23 | Completed | Medium | TRUE | 6 | 6
TASK0207 | Team Meeting | Alice Johnson | Finance | 2025-12-21 | 2026-01-10 | 2026-01-12 | Completed | Medium | TRUE | 2 | 5
TASK0208 | Security Patch | Frank Wilson | Finance | 2025-11-20 | 2025-12-05 | 2025-12-06 | Completed | Low | TRUE | 1 | 5
TASK0209 | Market Analysis | James Anderson | Sales | 2025-08-25 | 2025-09-06 | 2025-09-09 | Completed | Medium | TRUE | 3 | 7
TASK0210 | Quarterly Report | Carol White | IT | 2026-03-21 | 2026-04-05 |  | Overdue | Medium | TRUE | 6 | 6
TASK0211 | Product Launch | Nathan Clark | Operations | 2025-12-04 | 2025-12-24 |  | Cancelled | Medium | FALSE | 0 | 5
TASK0212 | Security Patch | Carol White | IT | 2025-11-29 | 2025-12-12 | 2025-12-14 | Completed | Low | TRUE | 2 | 4
TASK0213 | Security Patch | Nathan Clark | Operations | 2026-02-13 | 2026-02-24 | 2026-02-26 | Completed | Medium | TRUE | 2 | 6
TASK0214 | Risk Assessment | Carol White | IT | 2025-07-18 | 2025-07-27 | 2025-07-26 | Completed | High | FALSE | 0 | 7
TASK0215 | Security Patch | Maria Harris | IT | 2025-10-26 | 2025-11-06 |  | In Progress | Medium | FALSE | 0 | 1
TASK0216 | Dashboard Setup | Alice Johnson | Finance | 2026-02-27 | 2026-03-25 | 2026-03-30 | Completed | High | TRUE | 5 | 2
TASK0217 | Data Migration | David Lee | Operations | 2025-12-11 | 2025-12-17 | 2025-12-17 | Completed | Medium | FALSE | 0 | 9
TASK0218 | Client Presentation | Emma Brown | Sales | 2026-03-09 | 2026-03-26 |  | Cancelled | Medium | FALSE | 0 | 8
TASK0219 | Security Patch | Isabella Taylor | Operations | 2025-04-25 | 2025-05-06 |  | In Progress | Low | FALSE | 0 | 8
TASK0220 | Performance Review | James Anderson | Sales | 2025-07-18 | 2025-08-08 |  | Cancelled | High | FALSE | 0 | 6
TASK0221 | Market Analysis | Isabella Taylor | Operations | 2025-10-02 | 2025-10-14 |  | Overdue | Medium | TRUE | 9 | 1
TASK0222 | Stakeholder Report | Carol White | IT | 2025-09-03 | 2025-09-25 | 2025-09-27 | Completed | Low | TRUE | 2 | 10
TASK0223 | Process Improvement | Grace Chen | HR | 2026-02-15 | 2026-03-15 | 2026-03-22 | Completed | High | TRUE | 7 | 7
TASK0224 | Market Analysis | Emma Brown | Sales | 2025-12-11 | 2025-12-20 |  | Overdue | Low | TRUE | 15 | 9
TASK0225 | Contract Negotiation | Bob Martinez | HR | 2025-10-18 | 2025-11-07 | 2025-11-07 | Completed | Medium | FALSE | 0 | 5
TASK0226 | Data Migration | Emma Brown | Sales | 2025-04-09 | 2025-04-29 | 2025-05-05 | Completed | Medium | TRUE | 6 | 3
TASK0227 | Quarterly Report | Emma Brown | Sales | 2025-06-01 | 2025-06-16 | 2025-06-21 | Completed | High | TRUE | 5 | 9
TASK0228 | Contract Negotiation | Carol White | IT | 2025-02-22 | 2025-02-28 |  | Overdue | High | TRUE | 8 | 9
TASK0229 | Quarterly Report | Grace Chen | HR | 2025-07-10 | 2025-07-23 | 2025-07-27 | Completed | High | TRUE | 4 | 10
TASK0230 | Code Review | Nathan Clark | Operations | 2025-03-04 | 2025-03-22 | 2025-03-27 | Completed | Low | TRUE | 5 | 10
TASK0231 | Risk Assessment | David Lee | Operations | 2025-02-20 | 2025-03-14 |  | In Progress | Low | FALSE | 0 | 3
TASK0232 | Training Session | Maria Harris | IT | 2025-04-20 | 2025-05-06 | 2025-05-06 | Completed | High | FALSE | 0 | 6
TASK0233 | Market Analysis | Karen Thomas | Finance | 2025-01-15 | 2025-01-31 |  | Cancelled | Medium | FALSE | 0 | 1
TASK0234 | Compliance Audit | Bob Martinez | HR | 2025-05-24 | 2025-06-04 |  | Cancelled | Medium | FALSE | 0 | 1
TASK0235 | Vendor Evaluation | Grace Chen | HR | 2025-12-10 | 2025-12-22 | 2025-12-23 | Completed | Medium | TRUE | 1 | 4
TASK0236 | Process Improvement | Liam Jackson | HR | 2025-06-27 | 2025-07-08 |  | Overdue | Low | TRUE | 5 | 10
TASK0237 | Stakeholder Report | Liam Jackson | HR | 2025-05-01 | 2025-05-07 | 2025-05-10 | Completed | Low | TRUE | 3 | 3
TASK0238 | Product Launch | Nathan Clark | Operations | 2025-05-07 | 2025-05-11 | 2025-05-14 | Completed | Critical | TRUE | 3 | 4
TASK0239 | Dashboard Setup | Alice Johnson | Finance | 2025-02-14 | 2025-02-17 | 2025-02-18 | Completed | Critical | TRUE | 1 | 9
TASK0240 | System Upgrade | James Anderson | Sales | 2025-01-30 | 2025-02-25 | 2025-02-25 | Completed | Low | FALSE | 0 | 1
TASK0241 | Budget Review | Maria Harris | IT | 2025-07-10 | 2025-07-23 |  | Overdue | Medium | TRUE | 11 | 1
TASK0242 | Product Launch | Liam Jackson | HR | 2025-08-31 | 2025-09-23 |  | Overdue | High | TRUE | 14 | 3
TASK0243 | Client Presentation | Grace Chen | HR | 2025-10-19 | 2025-11-11 | 2025-11-18 | Completed | High | TRUE | 7 | 7
TASK0244 | Team Meeting | Bob Martinez | HR | 2025-01-20 | 2025-02-14 | 2025-02-12 | Completed | Critical | FALSE | 0 | 2
TASK0245 | Vendor Evaluation | Frank Wilson | Finance | 2025-03-22 | 2025-04-06 | 2025-04-13 | Completed | Low | TRUE | 7 | 10
TASK0246 | Stakeholder Report | Frank Wilson | Finance | 2025-07-24 | 2025-08-01 |  | Cancelled | Low | FALSE | 0 | 10
TASK0247 | Data Migration | James Anderson | Sales | 2025-11-27 | 2025-11-30 | 2025-12-03 | Completed | Medium | TRUE | 3 | 3
TASK0248 | Risk Assessment | Liam Jackson | HR | 2025-01-12 | 2025-01-29 |  | In Progress | Low | FALSE | 0 | 6
TASK0249 | Data Migration | Alice Johnson | Finance | 2025-05-10 | 2025-05-24 | 2025-05-24 | Completed | Medium | FALSE | 0 | 7
TASK0250 | Performance Review | Liam Jackson | HR | 2025-12-06 | 2025-12-16 |  | In Progress | Low | FALSE | 0 | 2
TASK0251 | Contract Negotiation | Bob Martinez | HR | 2025-11-01 | 2025-11-26 |  | In Progress | High | FALSE | 0 | 6
TASK0252 | Stakeholder Report | Alice Johnson | Finance | 2025-12-15 | 2026-01-04 | 2026-01-09 | Completed | Critical | TRUE | 5 | 6
TASK0253 | Risk Assessment | Carol White | IT | 2026-01-14 | 2026-02-11 | 2026-02-13 | Completed | Low | TRUE | 2 | 9
TASK0254 | Team Meeting | Alice Johnson | Finance | 2025-05-16 | 2025-06-06 |  | In Progress | High | FALSE | 0 | 5
TASK0255 | System Upgrade | Alice Johnson | Finance | 2025-07-10 | 2025-07-27 | 2025-07-26 | Completed | Critical | FALSE | 0 | 3
TASK0256 | Compliance Audit | Bob Martinez | HR | 2025-06-12 | 2025-06-21 | 2025-06-19 | Completed | Low | FALSE | 0 | 2
TASK0257 | Process Improvement | Henry Davis | IT | 2025-04-03 | 2025-04-27 |  | In Progress | High | FALSE | 0 | 4
TASK0258 | System Upgrade | Nathan Clark | Operations | 2025-01-23 | 2025-01-29 | 2025-01-31 | Completed | Low | TRUE | 2 | 8
TASK0259 | Dashboard Setup | James Anderson | Sales | 2025-02-16 | 2025-03-13 |  | Overdue | High | TRUE | 14 | 10
TASK0260 | Process Improvement | Henry Davis | IT | 2025-01-29 | 2025-02-09 | 2025-02-11 | Completed | Low | TRUE | 2 | 3
TASK0261 | Team Meeting | Olivia Lewis | Sales | 2025-12-27 | 2026-01-25 |  | Overdue | Medium | TRUE | 7 | 10
TASK0262 | Performance Review | Henry Davis | IT | 2025-12-29 | 2026-01-11 |  | Cancelled | Medium | FALSE | 0 | 10
TASK0263 | Client Presentation | Liam Jackson | HR | 2025-03-28 | 2025-04-26 | 2025-04-25 | Completed | High | FALSE | 0 | 6
TASK0264 | Vendor Evaluation | Liam Jackson | HR | 2025-07-03 | 2025-07-17 | 2025-07-19 | Completed | Medium | TRUE | 2 | 9
TASK0265 | Security Patch | Maria Harris | IT | 2025-06-26 | 2025-07-19 |  | Cancelled | Low | FALSE | 0 | 7
TASK0266 | Risk Assessment | Emma Brown | Sales | 2025-05-12 | 2025-06-01 |  | In Progress | Medium | FALSE | 0 | 4
TASK0267 | Budget Review | Frank Wilson | Finance | 2025-06-20 | 2025-07-07 | 2025-07-05 | Completed | High | FALSE | 0 | 6
TASK0268 | Stakeholder Report | Emma Brown | Sales | 2025-04-07 | 2025-05-01 | 2025-05-04 | Completed | Medium | TRUE | 3 | 2
TASK0269 | Market Analysis | Liam Jackson | HR | 2026-02-22 | 2026-03-01 |  | Overdue | High | TRUE | 12 | 8
TASK0270 | Policy Update | Bob Martinez | HR | 2025-06-26 | 2025-07-01 |  | Cancelled | Critical | FALSE | 0 | 7
TASK0271 | Quarterly Report | Nathan Clark | Operations | 2026-02-26 | 2026-03-19 | 2026-03-26 | Completed | Medium | TRUE | 7 | 7
TASK0272 | Stakeholder Report | Isabella Taylor | Operations | 2025-04-18 | 2025-05-04 |  | Overdue | Critical | TRUE | 4 | 2
TASK0273 | Compliance Audit | Grace Chen | HR | 2026-02-01 | 2026-02-27 |  | Overdue | Critical | TRUE | 19 | 10
TASK0274 | Team Meeting | Frank Wilson | Finance | 2025-07-15 | 2025-08-07 | 2025-08-06 | Completed | Medium | FALSE | 0 | 7
TASK0275 | Market Analysis | Henry Davis | IT | 2025-12-23 | 2026-01-18 |  | Cancelled | Medium | FALSE | 0 | 1
TASK0276 | Training Session | Maria Harris | IT | 2025-06-18 | 2025-06-24 |  | Overdue | Medium | TRUE | 2 | 2
TASK0277 | Contract Negotiation | Frank Wilson | Finance | 2026-03-18 | 2026-04-09 |  | In Progress | Medium | FALSE | 0 | 9
TASK0278 | Process Improvement | James Anderson | Sales | 2025-02-27 | 2025-03-05 | 2025-03-11 | Completed | Medium | TRUE | 6 | 2
TASK0279 | Compliance Audit | Liam Jackson | HR | 2025-11-25 | 2025-12-21 | 2025-12-19 | Completed | Low | FALSE | 0 | 8
TASK0280 | Vendor Evaluation | Alice Johnson | Finance | 2025-09-18 | 2025-09-25 | 2025-09-29 | Completed | Medium | TRUE | 4 | 5
TASK0281 | Quarterly Report | Karen Thomas | Finance | 2025-09-19 | 2025-10-04 |  | In Progress | High | FALSE | 0 | 2
TASK0282 | Training Session | Olivia Lewis | Sales | 2025-03-26 | 2025-04-11 | 2025-04-12 | Completed | High | TRUE | 1 | 6
TASK0283 | Client Presentation | Carol White | IT | 2025-12-31 | 2026-01-14 | 2026-01-21 | Completed | Low | TRUE | 7 | 1
TASK0284 | Stakeholder Report | David Lee | Operations | 2025-10-13 | 2025-10-25 |  | Overdue | Medium | TRUE | 9 | 1
TASK0285 | Performance Review | Carol White | IT | 2026-03-24 | 2026-04-08 | 2026-04-15 | Completed | Critical | TRUE | 7 | 5
TASK0286 | Product Launch | James Anderson | Sales | 2026-02-11 | 2026-02-24 | 2026-02-22 | Completed | Medium | FALSE | 0 | 1
TASK0287 | Data Migration | Emma Brown | Sales | 2025-01-27 | 2025-01-30 | 2025-02-05 | Completed | Low | TRUE | 6 | 10
TASK0288 | Stakeholder Report | Olivia Lewis | Sales | 2025-09-13 | 2025-10-05 |  | Cancelled | Medium | FALSE | 0 | 2
TASK0289 | Market Analysis | Frank Wilson | Finance | 2025-05-10 | 2025-05-21 | 2025-05-26 | Completed | Medium | TRUE | 5 | 2
TASK0290 | Budget Review | Carol White | IT | 2025-10-31 | 2025-11-26 |  | Cancelled | High | FALSE | 0 | 2
TASK0291 | Contract Negotiation | Bob Martinez | HR | 2026-01-14 | 2026-01-26 |  | Cancelled | Low | FALSE | 0 | 8
TASK0292 | Product Launch | Olivia Lewis | Sales | 2025-06-24 | 2025-07-11 |  | Overdue | High | TRUE | 19 | 4
TASK0293 | Risk Assessment | Nathan Clark | Operations | 2025-07-25 | 2025-08-09 |  | In Progress | Low | FALSE | 0 | 8
TASK0294 | System Upgrade | Maria Harris | IT | 2025-02-10 | 2025-03-04 | 2025-03-02 | Completed | High | FALSE | 0 | 4
TASK0295 | Policy Update | Isabella Taylor | Operations | 2025-10-03 | 2025-10-08 |  | Cancelled | Medium | FALSE | 0 | 8
TASK0296 | Market Analysis | Alice Johnson | Finance | 2026-01-04 | 2026-01-12 | 2026-01-13 | Completed | High | TRUE | 1 | 3
TASK0297 | Client Presentation | Henry Davis | IT | 2025-09-11 | 2025-09-15 |  | Cancelled | Low | FALSE | 0 | 1
TASK0298 | System Upgrade | Frank Wilson | Finance | 2025-09-13 | 2025-09-25 | 2025-10-02 | Completed | Critical | TRUE | 7 | 2
TASK0299 | Product Launch | David Lee | Operations | 2025-12-27 | 2026-01-22 | 2026-01-26 | Completed | Medium | TRUE | 4 | 6
TASK0300 | System Upgrade | James Anderson | Sales | 2025-02-10 | 2025-02-25 | 2025-02-25 | Completed | Low | FALSE | 0 | 9
TASK0301 | Compliance Audit | Grace Chen | HR | 2025-12-13 | 2025-12-19 | 2025-12-22 | Completed | Low | TRUE | 3 | 5
TASK0302 | Team Meeting | Grace Chen | HR | 2025-10-30 | 2025-11-06 |  | In Progress | High | FALSE | 0 | 2
TASK0303 | Team Meeting | Grace Chen | HR | 2025-11-18 | 2025-12-16 |  | In Progress | High | FALSE | 0 | 10
TASK0304 | Product Launch | Liam Jackson | HR | 2025-08-22 | 2025-08-25 | 2025-08-28 | Completed | High | TRUE | 3 | 2
TASK0305 | Product Launch | Olivia Lewis | Sales | 2025-08-04 | 2025-08-31 | 2025-09-02 | Completed | Low | TRUE | 2 | 5
TASK0306 | Security Patch | Olivia Lewis | Sales | 2025-10-14 | 2025-11-02 | 2025-10-31 | Completed | Medium | FALSE | 0 | 1
TASK0307 | Data Migration | Isabella Taylor | Operations | 2025-08-03 | 2025-08-25 |  | Overdue | Medium | TRUE | 2 | 10
TASK0308 | Code Review | Maria Harris | IT | 2025-07-12 | 2025-07-27 |  | Overdue | Medium | TRUE | 13 | 9
TASK0309 | Process Improvement | Carol White | IT | 2025-10-26 | 2025-11-19 | 2025-11-23 | Completed | Medium | TRUE | 4 | 9
TASK0310 | Contract Negotiation | Nathan Clark | Operations | 2026-01-01 | 2026-01-13 | 2026-01-16 | Completed | High | TRUE | 3 | 10
TASK0311 | Training Session | Alice Johnson | Finance | 2025-12-02 | 2025-12-14 | 2025-12-13 | Completed | Medium | FALSE | 0 | 8
TASK0312 | Client Presentation | Frank Wilson | Finance | 2026-02-07 | 2026-03-01 |  | Overdue | Medium | TRUE | 6 | 2
TASK0313 | Data Migration | Isabella Taylor | Operations | 2025-03-30 | 2025-04-12 | 2025-04-12 | Completed | Low | FALSE | 0 | 2
TASK0314 | Team Meeting | Emma Brown | Sales | 2025-11-15 | 2025-12-10 |  | Overdue | Low | TRUE | 4 | 6
TASK0315 | Performance Review | Liam Jackson | HR | 2025-05-04 | 2025-05-13 | 2025-05-14 | Completed | Medium | TRUE | 1 | 4
TASK0316 | System Upgrade | Frank Wilson | Finance | 2025-02-01 | 2025-02-15 |  | In Progress | Medium | FALSE | 0 | 2
TASK0317 | Policy Update | Henry Davis | IT | 2025-04-03 | 2025-04-18 |  | Overdue | Medium | TRUE | 9 | 2
TASK0318 | Team Meeting | Maria Harris | IT | 2025-04-15 | 2025-04-30 | 2025-05-01 | Completed | High | TRUE | 1 | 2
TASK0319 | Compliance Audit | Frank Wilson | Finance | 2025-03-24 | 2025-04-03 |  | Overdue | High | TRUE | 7 | 2
TASK0320 | Performance Review | Bob Martinez | HR | 2026-02-10 | 2026-02-19 | 2026-02-22 | Completed | Medium | TRUE | 3 | 9
TASK0321 | Contract Negotiation | Liam Jackson | HR | 2025-01-11 | 2025-02-06 | 2025-02-10 | Completed | Low | TRUE | 4 | 7
TASK0322 | Code Review | Olivia Lewis | Sales | 2025-08-15 | 2025-09-08 |  | Overdue | Medium | TRUE | 7 | 9
TASK0323 | Risk Assessment | Grace Chen | HR | 2025-07-30 | 2025-08-15 | 2025-08-17 | Completed | Critical | TRUE | 2 | 6
TASK0324 | Policy Update | Grace Chen | HR | 2026-03-22 | 2026-03-27 |  | In Progress | Medium | FALSE | 0 | 7
TASK0325 | Dashboard Setup | Karen Thomas | Finance | 2026-03-24 | 2026-04-14 |  | Overdue | Medium | TRUE | 17 | 3
TASK0326 | Security Patch | Bob Martinez | HR | 2025-05-01 | 2025-05-26 | 2025-05-30 | Completed | High | TRUE | 4 | 9
TASK0327 | Contract Negotiation | James Anderson | Sales | 2025-05-14 | 2025-05-22 |  | In Progress | High | FALSE | 0 | 10
TASK0328 | Code Review | Carol White | IT | 2025-12-11 | 2025-12-24 | 2025-12-22 | Completed | High | FALSE | 0 | 7
TASK0329 | Team Meeting | Maria Harris | IT | 2025-04-12 | 2025-05-06 | 2025-05-13 | Completed | Medium | TRUE | 7 | 8
TASK0330 | Vendor Evaluation | David Lee | Operations | 2026-03-26 | 2026-04-19 | 2026-04-21 | Completed | Low | TRUE | 2 | 3
TASK0331 | Data Migration | David Lee | Operations | 2025-01-03 | 2025-01-17 |  | Cancelled | High | FALSE | 0 | 6
TASK0332 | Contract Negotiation | Olivia Lewis | Sales | 2025-12-14 | 2026-01-01 |  | Overdue | High | TRUE | 8 | 5
TASK0333 | Training Session | Liam Jackson | HR | 2025-09-15 | 2025-09-27 | 2025-10-04 | Completed | High | TRUE | 7 | 9
TASK0334 | Security Patch | Nathan Clark | Operations | 2025-12-31 | 2026-01-23 | 2026-01-21 | Completed | High | FALSE | 0 | 1
TASK0335 | Client Presentation | Carol White | IT | 2025-03-26 | 2025-04-02 | 2025-04-01 | Completed | Medium | FALSE | 0 | 4
TASK0336 | Product Launch | Isabella Taylor | Operations | 2025-10-17 | 2025-11-08 |  | Overdue | Medium | TRUE | 14 | 5
TASK0337 | Client Presentation | Carol White | IT | 2026-02-20 | 2026-02-24 | 2026-02-24 | Completed | Medium | FALSE | 0 | 10
TASK0338 | Process Improvement | Olivia Lewis | Sales | 2025-07-30 | 2025-08-05 | 2025-08-05 | Completed | Medium | FALSE | 0 | 8
TASK0339 | Team Meeting | Carol White | IT | 2025-12-25 | 2026-01-02 | 2026-01-09 | Completed | Medium | TRUE | 7 | 2
TASK0340 | System Upgrade | Isabella Taylor | Operations | 2025-04-25 | 2025-05-05 | 2025-05-04 | Completed | High | FALSE | 0 | 9
TASK0341 | Process Improvement | Alice Johnson | Finance | 2026-01-17 | 2026-02-06 | 2026-02-07 | Completed | Medium | TRUE | 1 | 10
TASK0342 | Process Improvement | David Lee | Operations | 2025-12-19 | 2025-12-26 |  | In Progress | High | FALSE | 0 | 1
TASK0343 | Policy Update | David Lee | Operations | 2025-02-02 | 2025-02-11 |  | Overdue | Low | TRUE | 10 | 3
TASK0344 | Contract Negotiation | Alice Johnson | Finance | 2025-08-30 | 2025-09-22 | 2025-09-26 | Completed | Low | TRUE | 4 | 1
TASK0345 | Security Patch | Bob Martinez | HR | 2026-03-15 | 2026-03-29 |  | Cancelled | Medium | FALSE | 0 | 2
TASK0346 | Quarterly Report | Alice Johnson | Finance | 2026-01-05 | 2026-01-12 |  | Overdue | Medium | TRUE | 15 | 9
TASK0347 | Compliance Audit | James Anderson | Sales | 2025-08-15 | 2025-09-05 | 2025-09-08 | Completed | High | TRUE | 3 | 3
TASK0348 | Market Analysis | Henry Davis | IT | 2026-02-15 | 2026-03-11 |  | Overdue | High | TRUE | 5 | 6
TASK0349 | Dashboard Setup | Liam Jackson | HR | 2025-03-26 | 2025-04-07 | 2025-04-12 | Completed | Medium | TRUE | 5 | 8
TASK0350 | Team Meeting | Grace Chen | HR | 2026-03-19 | 2026-04-01 |  | Cancelled | Medium | FALSE | 0 | 10
TASK0351 | Market Analysis | Frank Wilson | Finance | 2025-04-10 | 2025-04-15 | 2025-04-18 | Completed | Medium | TRUE | 3 | 1
TASK0352 | Dashboard Setup | Grace Chen | HR | 2025-09-28 | 2025-10-11 | 2025-10-15 | Completed | Low | TRUE | 4 | 6
TASK0353 | Dashboard Setup | Olivia Lewis | Sales | 2025-04-04 | 2025-04-16 | 2025-04-16 | Completed | Low | FALSE | 0 | 3
TASK0354 | Quarterly Report | James Anderson | Sales | 2025-07-24 | 2025-08-01 |  | Overdue | Medium | TRUE | 18 | 10
TASK0355 | Budget Review | Karen Thomas | Finance | 2025-07-23 | 2025-08-04 | 2025-08-10 | Completed | Medium | TRUE | 6 | 5
TASK0356 | Code Review | Maria Harris | IT | 2026-01-26 | 2026-01-30 | 2026-01-31 | Completed | Critical | TRUE | 1 | 5
TASK0357 | Security Patch | Liam Jackson | HR | 2025-11-27 | 2025-12-23 |  | Overdue | High | TRUE | 6 | 3
TASK0358 | Client Presentation | David Lee | Operations | 2025-12-24 | 2026-01-02 |  | Overdue | Medium | TRUE | 8 | 8
TASK0359 | Contract Negotiation | Alice Johnson | Finance | 2025-06-17 | 2025-07-10 |  | In Progress | Low | FALSE | 0 | 2
TASK0360 | Budget Review | Nathan Clark | Operations | 2025-10-16 | 2025-10-27 | 2025-10-27 | Completed | Medium | FALSE | 0 | 6
TASK0361 | Market Analysis | Alice Johnson | Finance | 2025-09-18 | 2025-09-24 | 2025-09-23 | Completed | Low | FALSE | 0 | 9
TASK0362 | Policy Update | David Lee | Operations | 2025-05-30 | 2025-06-24 |  | Cancelled | Low | FALSE | 0 | 10
TASK0363 | System Upgrade | Carol White | IT | 2025-06-21 | 2025-06-25 | 2025-06-23 | Completed | High | FALSE | 0 | 2
TASK0364 | Policy Update | Olivia Lewis | Sales | 2025-11-27 | 2025-12-15 | 2025-12-13 | Completed | Critical | FALSE | 0 | 6
TASK0365 | Contract Negotiation | Liam Jackson | HR | 2025-07-17 | 2025-08-03 |  | Overdue | Medium | TRUE | 18 | 4
TASK0366 | Risk Assessment | Karen Thomas | Finance | 2025-01-31 | 2025-02-07 | 2025-02-09 | Completed | Medium | TRUE | 2 | 2
TASK0367 | Client Presentation | Liam Jackson | HR | 2025-12-26 | 2026-01-20 | 2026-01-24 | Completed | High | TRUE | 4 | 8
TASK0368 | Budget Review | Emma Brown | Sales | 2026-02-01 | 2026-02-24 |  | Overdue | Medium | TRUE | 4 | 9
TASK0369 | Code Review | Emma Brown | Sales | 2025-02-20 | 2025-03-02 |  | In Progress | High | FALSE | 0 | 7
TASK0370 | Data Migration | Olivia Lewis | Sales | 2025-10-07 | 2025-10-22 |  | In Progress | High | FALSE | 0 | 6
TASK0371 | Vendor Evaluation | James Anderson | Sales | 2025-10-05 | 2025-10-26 | 2025-10-29 | Completed | Medium | TRUE | 3 | 4
TASK0372 | Process Improvement | Karen Thomas | Finance | 2025-07-15 | 2025-07-20 | 2025-07-27 | Completed | Critical | TRUE | 7 | 1
TASK0373 | Client Presentation | David Lee | Operations | 2026-01-16 | 2026-02-10 |  | Overdue | Medium | TRUE | 9 | 8
TASK0374 | Risk Assessment | Isabella Taylor | Operations | 2025-02-07 | 2025-02-26 | 2025-03-03 | Completed | Medium | TRUE | 5 | 6
TASK0375 | Contract Negotiation | Nathan Clark | Operations | 2026-03-26 | 2026-04-17 | 2026-04-16 | Completed | Medium | FALSE | 0 | 7
TASK0376 | Code Review | Bob Martinez | HR | 2025-05-31 | 2025-06-16 | 2025-06-19 | Completed | Medium | TRUE | 3 | 6
TASK0377 | Team Meeting | Henry Davis | IT | 2025-07-11 | 2025-07-19 | 2025-07-18 | Completed | Low | FALSE | 0 | 6
TASK0378 | Dashboard Setup | Bob Martinez | HR | 2025-08-31 | 2025-09-22 | 2025-09-27 | Completed | Critical | TRUE | 5 | 4
TASK0379 | Code Review | Alice Johnson | Finance | 2026-03-12 | 2026-03-19 | 2026-03-21 | Completed | Medium | TRUE | 2 | 2
TASK0380 | Process Improvement | James Anderson | Sales | 2025-05-11 | 2025-06-03 |  | In Progress | High | FALSE | 0 | 4
TASK0381 | Team Meeting | Carol White | IT | 2025-12-07 | 2025-12-23 | 2025-12-29 | Completed | Low | TRUE | 6 | 3
TASK0382 | Compliance Audit | Frank Wilson | Finance | 2025-04-23 | 2025-05-14 | 2025-05-14 | Completed | High | FALSE | 0 | 10
TASK0383 | System Upgrade | James Anderson | Sales | 2025-08-26 | 2025-09-07 |  | Cancelled | Low | FALSE | 0 | 6
TASK0384 | Client Presentation | James Anderson | Sales | 2025-06-20 | 2025-07-07 |  | Cancelled | Low | FALSE | 0 | 4
TASK0385 | Client Presentation | Karen Thomas | Finance | 2026-03-20 | 2026-04-04 | 2026-04-11 | Completed | High | TRUE | 7 | 9
TASK0386 | Quarterly Report | Nathan Clark | Operations | 2025-05-25 | 2025-06-14 | 2025-06-17 | Completed | Medium | TRUE | 3 | 10
TASK0387 | Process Improvement | Bob Martinez | HR | 2025-07-03 | 2025-07-24 |  | In Progress | Medium | FALSE | 0 | 6
TASK0388 | System Upgrade | Liam Jackson | HR | 2025-07-13 | 2025-07-21 | 2025-07-24 | Completed | High | TRUE | 3 | 6
TASK0389 | Dashboard Setup | Maria Harris | IT | 2026-03-20 | 2026-04-06 | 2026-04-05 | Completed | Medium | FALSE | 0 | 2
TASK0390 | Vendor Evaluation | Alice Johnson | Finance | 2026-02-06 | 2026-02-16 | 2026-02-20 | Completed | High | TRUE | 4 | 3
TASK0391 | Quarterly Report | Alice Johnson | Finance | 2025-01-11 | 2025-02-05 |  | In Progress | Critical | FALSE | 0 | 9
TASK0392 | Vendor Evaluation | Bob Martinez | HR | 2025-07-19 | 2025-08-01 | 2025-07-30 | Completed | Medium | FALSE | 0 | 2
TASK0393 | Product Launch | Grace Chen | HR | 2025-03-22 | 2025-04-10 | 2025-04-17 | Completed | Low | TRUE | 7 | 9
TASK0394 | Policy Update | Frank Wilson | Finance | 2025-10-24 | 2025-10-30 | 2025-11-04 | Completed | High | TRUE | 5 | 6
TASK0395 | Training Session | Carol White | IT | 2025-05-16 | 2025-06-12 | 2025-06-14 | Completed | Low | TRUE | 2 | 6
TASK0396 | System Upgrade | Liam Jackson | HR | 2025-06-08 | 2025-06-24 | 2025-06-29 | Completed | High | TRUE | 5 | 4
TASK0397 | Client Presentation | Frank Wilson | Finance | 2025-10-02 | 2025-10-22 |  | In Progress | Medium | FALSE | 0 | 1
TASK0398 | System Upgrade | Liam Jackson | HR | 2026-01-25 | 2026-02-09 |  | In Progress | Low | FALSE | 0 | 1
TASK0399 | Stakeholder Report | James Anderson | Sales | 2025-04-11 | 2025-04-29 | 2025-05-01 | Completed | High | TRUE | 2 | 7
TASK0400 | Training Session | Carol White | IT | 2026-02-21 | 2026-03-07 |  | Overdue | High | TRUE | 4 | 5
TASK0401 | Product Launch | James Anderson | Sales | 2026-03-05 | 2026-03-21 |  | Cancelled | Critical | FALSE | 0 | 10
TASK0402 | Code Review | Alice Johnson | Finance | 2025-04-15 | 2025-05-14 |  | Cancelled | Medium | FALSE | 0 | 2
TASK0403 | Budget Review | Carol White | IT | 2025-10-04 | 2025-11-01 |  | Overdue | Critical | TRUE | 12 | 6
TASK0404 | Vendor Evaluation | Henry Davis | IT | 2025-11-29 | 2025-12-21 | 2025-12-19 | Completed | Medium | FALSE | 0 | 5
TASK0405 | Security Patch | Karen Thomas | Finance | 2025-08-18 | 2025-09-04 | 2025-09-05 | Completed | Low | TRUE | 1 | 8
TASK0406 | Market Analysis | Nathan Clark | Operations | 2025-03-20 | 2025-04-02 | 2025-04-02 | Completed | Medium | FALSE | 0 | 10
TASK0407 | Budget Review | Karen Thomas | Finance | 2025-04-07 | 2025-05-05 |  | Overdue | Low | TRUE | 17 | 5
TASK0408 | Training Session | James Anderson | Sales | 2025-10-06 | 2025-10-21 | 2025-10-28 | Completed | Low | TRUE | 7 | 4
TASK0409 | Product Launch | Bob Martinez | HR | 2025-03-09 | 2025-03-24 |  | Cancelled | Medium | FALSE | 0 | 3
TASK0410 | Budget Review | Bob Martinez | HR | 2025-07-06 | 2025-07-21 | 2025-07-26 | Completed | Medium | TRUE | 5 | 4
TASK0411 | Policy Update | Liam Jackson | HR | 2025-11-26 | 2025-12-13 | 2025-12-14 | Completed | High | TRUE | 1 | 1
TASK0412 | Vendor Evaluation | Maria Harris | IT | 2025-03-27 | 2025-04-02 |  | Cancelled | Medium | FALSE | 0 | 3
TASK0413 | Data Migration | Frank Wilson | Finance | 2025-03-10 | 2025-03-18 | 2025-03-22 | Completed | Medium | TRUE | 4 | 9
TASK0414 | Client Presentation | Bob Martinez | HR | 2025-07-18 | 2025-08-08 | 2025-08-10 | Completed | High | TRUE | 2 | 1
TASK0415 | Vendor Evaluation | Isabella Taylor | Operations | 2025-10-04 | 2025-10-15 | 2025-10-16 | Completed | High | TRUE | 1 | 6
TASK0416 | Risk Assessment | Emma Brown | Sales | 2025-04-22 | 2025-05-04 | 2025-05-06 | Completed | High | TRUE | 2 | 7
TASK0417 | Policy Update | Emma Brown | Sales | 2025-08-27 | 2025-09-04 | 2025-09-07 | Completed | Low | TRUE | 3 | 4
TASK0418 | Stakeholder Report | Carol White | IT | 2025-07-09 | 2025-07-31 | 2025-07-30 | Completed | Medium | FALSE | 0 | 1
TASK0419 | Market Analysis | Bob Martinez | HR | 2025-09-28 | 2025-10-07 | 2025-10-12 | Completed | Low | TRUE | 5 | 8
TASK0420 | Data Migration | Nathan Clark | Operations | 2026-02-23 | 2026-03-24 |  | In Progress | Medium | FALSE | 0 | 3
TASK0421 | Product Launch | Olivia Lewis | Sales | 2025-08-30 | 2025-09-05 | 2025-09-10 | Completed | Critical | TRUE | 5 | 10
TASK0422 | Risk Assessment | Frank Wilson | Finance | 2025-02-16 | 2025-03-13 | 2025-03-16 | Completed | Low | TRUE | 3 | 1
TASK0423 | Risk Assessment | Emma Brown | Sales | 2025-01-09 | 2025-01-15 |  | Cancelled | Medium | FALSE | 0 | 3
TASK0424 | Dashboard Setup | David Lee | Operations | 2025-08-15 | 2025-08-19 | 2025-08-17 | Completed | Low | FALSE | 0 | 1
TASK0425 | Market Analysis | Isabella Taylor | Operations | 2026-03-14 | 2026-04-12 | 2026-04-12 | Completed | Low | FALSE | 0 | 5
TASK0426 | System Upgrade | Nathan Clark | Operations | 2025-05-06 | 2025-05-20 | 2025-05-26 | Completed | Low | TRUE | 6 | 6
TASK0427 | Client Presentation | Maria Harris | IT | 2025-03-25 | 2025-04-16 |  | Cancelled | Medium | FALSE | 0 | 4
TASK0428 | Client Presentation | Emma Brown | Sales | 2025-11-18 | 2025-12-09 | 2025-12-11 | Completed | Critical | TRUE | 2 | 6
TASK0429 | Performance Review | Carol White | IT | 2025-06-30 | 2025-07-12 | 2025-07-13 | Completed | Medium | TRUE | 1 | 6
TASK0430 | Stakeholder Report | Karen Thomas | Finance | 2025-01-26 | 2025-02-13 | 2025-02-13 | Completed | Medium | FALSE | 0 | 2
TASK0431 | Quarterly Report | David Lee | Operations | 2025-09-12 | 2025-09-28 | 2025-10-01 | Completed | Low | TRUE | 3 | 8
TASK0432 | System Upgrade | Bob Martinez | HR | 2025-05-14 | 2025-06-07 |  | Overdue | High | TRUE | 18 | 4
TASK0433 | Security Patch | Olivia Lewis | Sales | 2025-11-05 | 2025-12-04 |  | In Progress | Medium | FALSE | 0 | 5
TASK0434 | Policy Update | Henry Davis | IT | 2025-08-28 | 2025-09-21 | 2025-09-20 | Completed | High | FALSE | 0 | 4
TASK0435 | Contract Negotiation | Grace Chen | HR | 2025-04-30 | 2025-05-09 |  | Cancelled | Critical | FALSE | 0 | 7
TASK0436 | Data Migration | Alice Johnson | Finance | 2026-01-07 | 2026-01-10 | 2026-01-11 | Completed | High | TRUE | 1 | 4
TASK0437 | Performance Review | Emma Brown | Sales | 2026-03-18 | 2026-03-30 | 2026-03-31 | Completed | High | TRUE | 1 | 5
TASK0438 | Client Presentation | Emma Brown | Sales | 2025-05-12 | 2025-06-04 | 2025-06-07 | Completed | Critical | TRUE | 3 | 3
TASK0439 | Product Launch | Olivia Lewis | Sales | 2026-02-24 | 2026-03-07 | 2026-03-05 | Completed | Low | FALSE | 0 | 8
TASK0440 | Stakeholder Report | Liam Jackson | HR | 2025-03-18 | 2025-04-01 |  | Overdue | Medium | TRUE | 3 | 5
TASK0441 | Code Review | Liam Jackson | HR | 2025-08-10 | 2025-08-15 | 2025-08-22 | Completed | Low | TRUE | 7 | 1
TASK0442 | Vendor Evaluation | Olivia Lewis | Sales | 2025-03-02 | 2025-03-05 | 2025-03-09 | Completed | Medium | TRUE | 4 | 3
TASK0443 | Stakeholder Report | Liam Jackson | HR | 2025-06-06 | 2025-06-11 |  | In Progress | Medium | FALSE | 0 | 6
TASK0444 | Vendor Evaluation | Liam Jackson | HR | 2025-07-21 | 2025-08-05 | 2025-08-05 | Completed | Medium | FALSE | 0 | 3
TASK0445 | Team Meeting | Olivia Lewis | Sales | 2025-05-02 | 2025-05-28 |  | Overdue | Medium | TRUE | 17 | 4
TASK0446 | Budget Review | Nathan Clark | Operations | 2025-07-07 | 2025-07-22 | 2025-07-22 | Completed | High | FALSE | 0 | 5
TASK0447 | Contract Negotiation | Frank Wilson | Finance | 2025-09-12 | 2025-09-29 | 2025-10-01 | Completed | High | TRUE | 2 | 6
TASK0448 | Quarterly Report | Henry Davis | IT | 2025-12-20 | 2026-01-05 |  | Cancelled | High | FALSE | 0 | 9
TASK0449 | Product Launch | Olivia Lewis | Sales | 2025-09-09 | 2025-09-16 | 2025-09-16 | Completed | Low | FALSE | 0 | 10
TASK0450 | Code Review | Maria Harris | IT | 2026-02-28 | 2026-03-06 | 2026-03-07 | Completed | Medium | TRUE | 1 | 2
TASK0451 | Training Session | Isabella Taylor | Operations | 2025-03-23 | 2025-04-17 | 2025-04-15 | Completed | Medium | FALSE | 0 | 4
TASK0452 | Vendor Evaluation | Bob Martinez | HR | 2025-06-20 | 2025-06-26 | 2025-06-27 | Completed | Medium | TRUE | 1 | 1
TASK0453 | Compliance Audit | Olivia Lewis | Sales | 2025-02-24 | 2025-03-14 | 2025-03-15 | Completed | Low | TRUE | 1 | 3
TASK0454 | System Upgrade | Karen Thomas | Finance | 2025-11-21 | 2025-12-20 | 2025-12-25 | Completed | Medium | TRUE | 5 | 8
TASK0455 | Code Review | Grace Chen | HR | 2026-02-19 | 2026-02-24 | 2026-03-02 | Completed | Low | TRUE | 6 | 8
TASK0456 | Compliance Audit | Bob Martinez | HR | 2025-05-27 | 2025-06-08 |  | Cancelled | Low | FALSE | 0 | 4
TASK0457 | Training Session | Karen Thomas | Finance | 2026-02-09 | 2026-03-07 | 2026-03-07 | Completed | Medium | FALSE | 0 | 5
TASK0458 | System Upgrade | Henry Davis | IT | 2025-10-22 | 2025-10-27 | 2025-10-28 | Completed | Critical | TRUE | 1 | 8
TASK0459 | Stakeholder Report | Isabella Taylor | Operations | 2025-12-03 | 2025-12-16 |  | Cancelled | Critical | FALSE | 0 | 7
TASK0460 | Performance Review | Nathan Clark | Operations | 2026-01-27 | 2026-02-13 | 2026-02-15 | Completed | High | TRUE | 2 | 10
TASK0461 | Data Migration | Emma Brown | Sales | 2025-10-27 | 2025-11-09 | 2025-11-08 | Completed | Critical | FALSE | 0 | 6
TASK0462 | Performance Review | Carol White | IT | 2025-04-21 | 2025-05-03 |  | In Progress | High | FALSE | 0 | 4
TASK0463 | Data Migration | Karen Thomas | Finance | 2025-09-22 | 2025-10-02 | 2025-10-09 | Completed | Medium | TRUE | 7 | 6
TASK0464 | Performance Review | Emma Brown | Sales | 2025-01-27 | 2025-02-18 |  | Overdue | Low | TRUE | 9 | 6
TASK0465 | Quarterly Report | Olivia Lewis | Sales | 2025-02-11 | 2025-02-25 | 2025-02-28 | Completed | Low | TRUE | 3 | 7
TASK0466 | Budget Review | Alice Johnson | Finance | 2025-11-22 | 2025-12-17 | 2025-12-23 | Completed | Medium | TRUE | 6 | 2
TASK0467 | Training Session | Isabella Taylor | Operations | 2026-01-15 | 2026-02-01 |  | Overdue | Medium | TRUE | 17 | 7
TASK0468 | Team Meeting | Alice Johnson | Finance | 2026-01-23 | 2026-02-15 | 2026-02-19 | Completed | Medium | TRUE | 4 | 1
TASK0469 | Security Patch | Henry Davis | IT | 2025-11-13 | 2025-11-24 | 2025-11-24 | Completed | High | FALSE | 0 | 5
TASK0470 | Budget Review | Karen Thomas | Finance | 2025-03-31 | 2025-04-10 |  | Overdue | Low | TRUE | 6 | 1
TASK0471 | Client Presentation | Carol White | IT | 2025-05-19 | 2025-06-07 |  | In Progress | Medium | FALSE | 0 | 10
TASK0472 | Quarterly Report | Emma Brown | Sales | 2026-02-09 | 2026-02-12 |  | In Progress | Critical | FALSE | 0 | 7
TASK0473 | Client Presentation | Olivia Lewis | Sales | 2025-08-01 | 2025-08-10 |  | Overdue | Low | TRUE | 10 | 8
TASK0474 | Training Session | Nathan Clark | Operations | 2025-07-14 | 2025-07-24 | 2025-07-27 | Completed | High | TRUE | 3 | 5
TASK0475 | Performance Review | James Anderson | Sales | 2025-06-23 | 2025-06-26 | 2025-06-25 | Completed | Low | FALSE | 0 | 9
TASK0476 | System Upgrade | Liam Jackson | HR | 2025-12-10 | 2026-01-04 | 2026-01-06 | Completed | High | TRUE | 2 | 4
TASK0477 | Quarterly Report | James Anderson | Sales | 2025-07-01 | 2025-07-24 | 2025-07-22 | Completed | Critical | FALSE | 0 | 10
TASK0478 | System Upgrade | Emma Brown | Sales | 2025-03-31 | 2025-04-06 | 2025-04-09 | Completed | Low | TRUE | 3 | 3
TASK0479 | Compliance Audit | Grace Chen | HR | 2026-01-08 | 2026-01-19 | 2026-01-18 | Completed | Medium | FALSE | 0 | 5
TASK0480 | Policy Update | Liam Jackson | HR | 2025-06-16 | 2025-07-04 |  | Overdue | Medium | TRUE | 11 | 5
TASK0481 | Product Launch | James Anderson | Sales | 2025-11-24 | 2025-12-22 | 2025-12-22 | Completed | High | FALSE | 0 | 1
TASK0482 | Security Patch | Alice Johnson | Finance | 2026-01-11 | 2026-01-16 |  | Overdue | Critical | TRUE | 2 | 8
TASK0483 | Security Patch | Emma Brown | Sales | 2025-04-16 | 2025-05-01 |  | Overdue | Critical | TRUE | 11 | 1
TASK0484 | Quarterly Report | Liam Jackson | HR | 2025-08-14 | 2025-09-10 | 2025-09-17 | Completed | Medium | TRUE | 7 | 5
TASK0485 | Data Migration | Grace Chen | HR | 2025-08-03 | 2025-08-08 | 2025-08-14 | Completed | Low | TRUE | 6 | 2
TASK0486 | Policy Update | Bob Martinez | HR | 2025-07-08 | 2025-07-12 | 2025-07-13 | Completed | Medium | TRUE | 1 | 7
TASK0487 | Vendor Evaluation | Frank Wilson | Finance | 2025-05-18 | 2025-06-10 | 2025-06-10 | Completed | Medium | FALSE | 0 | 6
TASK0488 | Client Presentation | Maria Harris | IT | 2025-09-28 | 2025-10-16 |  | Overdue | High | TRUE | 3 | 4
TASK0489 | Process Improvement | Grace Chen | HR | 2025-03-09 | 2025-03-27 | 2025-03-25 | Completed | Low | FALSE | 0 | 7
TASK0490 | Data Migration | Bob Martinez | HR | 2025-01-21 | 2025-02-02 |  | Cancelled | Medium | FALSE | 0 | 1
TASK0491 | Dashboard Setup | Liam Jackson | HR | 2026-01-15 | 2026-01-27 |  | In Progress | Critical | FALSE | 0 | 4
TASK0492 | Market Analysis | Isabella Taylor | Operations | 2025-04-26 | 2025-05-09 |  | Cancelled | Medium | FALSE | 0 | 1
TASK0493 | Training Session | Carol White | IT | 2025-04-10 | 2025-05-04 |  | In Progress | High | FALSE | 0 | 7
TASK0494 | Client Presentation | Karen Thomas | Finance | 2025-04-22 | 2025-05-09 |  | Overdue | Low | TRUE | 11 | 8
TASK0495 | Product Launch | Liam Jackson | HR | 2025-11-03 | 2025-11-30 |  | Cancelled | High | FALSE | 0 | 3
TASK0496 | Risk Assessment | Olivia Lewis | Sales | 2025-06-06 | 2025-06-11 | 2025-06-12 | Completed | Medium | TRUE | 1 | 10
TASK0497 | Code Review | David Lee | Operations | 2025-12-10 | 2025-12-16 | 2025-12-14 | Completed | Medium | FALSE | 0 | 9
TASK0498 | Code Review | Carol White | IT | 2026-02-22 | 2026-03-16 | 2026-03-15 | Completed | Medium | FALSE | 0 | 2
TASK0499 | Dashboard Setup | Bob Martinez | HR | 2025-01-27 | 2025-02-21 |  | In Progress | Medium | FALSE | 0 | 3
TASK0500 | Code Review | Nathan Clark | Operations | 2025-11-10 | 2025-11-18 | 2025-11-25 | Completed | Medium | TRUE | 7 | 8
TASK0501 | Vendor Evaluation | Alice Johnson | Finance | 2025-12-07 | 2025-12-20 | 2025-12-27 | Completed | Medium | TRUE | 7 | 6
TASK0502 | Compliance Audit | Henry Davis | IT | 2025-08-05 | 2025-08-30 | 2025-09-02 | Completed | High | TRUE | 3 | 2
TASK0503 | Dashboard Setup | Alice Johnson | Finance | 2025-09-21 | 2025-10-03 |  | In Progress | Medium | FALSE | 0 | 1
TASK0504 | Dashboard Setup | James Anderson | Sales | 2025-12-26 | 2026-01-14 |  | In Progress | Medium | FALSE | 0 | 3
TASK0505 | System Upgrade | Olivia Lewis | Sales | 2025-05-03 | 2025-05-28 | 2025-05-31 | Completed | Medium | TRUE | 3 | 6
TASK0506 | Performance Review | Olivia Lewis | Sales | 2025-09-24 | 2025-10-01 | 2025-10-01 | Completed | Medium | FALSE | 0 | 9
TASK0507 | Market Analysis | Alice Johnson | Finance | 2025-09-24 | 2025-10-04 |  | In Progress | Low | FALSE | 0 | 8
TASK0508 | Security Patch | Frank Wilson | Finance | 2025-06-16 | 2025-07-03 |  | Overdue | Medium | TRUE | 6 | 1
TASK0509 | Team Meeting | Frank Wilson | Finance | 2025-03-14 | 2025-03-27 | 2025-04-03 | Completed | Critical | TRUE | 7 | 4
TASK0510 | System Upgrade | Olivia Lewis | Sales | 2025-04-12 | 2025-04-24 | 2025-04-22 | Completed | Medium | FALSE | 0 | 10
TASK0511 | Policy Update | Maria Harris | IT | 2025-09-16 | 2025-09-21 |  | Overdue | High | TRUE | 18 | 9
TASK0512 | Budget Review | James Anderson | Sales | 2026-03-11 | 2026-04-07 | 2026-04-14 | Completed | Low | TRUE | 7 | 2
TASK0513 | Client Presentation | Nathan Clark | Operations | 2025-12-03 | 2025-12-28 |  | In Progress | Medium | FALSE | 0 | 7
TASK0514 | Dashboard Setup | Karen Thomas | Finance | 2026-03-04 | 2026-03-20 |  | In Progress | Critical | FALSE | 0 | 5
TASK0515 | Code Review | Maria Harris | IT | 2025-10-24 | 2025-11-21 | 2025-11-19 | Completed | High | FALSE | 0 | 6
TASK0516 | Process Improvement | Henry Davis | IT | 2026-01-28 | 2026-02-03 | 2026-02-03 | Completed | Medium | FALSE | 0 | 7
TASK0517 | System Upgrade | Bob Martinez | HR | 2025-01-10 | 2025-01-19 |  | Overdue | High | TRUE | 18 | 4
TASK0518 | Training Session | Isabella Taylor | Operations | 2025-12-30 | 2026-01-11 | 2026-01-16 | Completed | High | TRUE | 5 | 4
TASK0519 | Code Review | James Anderson | Sales | 2025-01-23 | 2025-02-19 | 2025-02-26 | Completed | Low | TRUE | 7 | 10
TASK0520 | Contract Negotiation | Maria Harris | IT | 2025-08-20 | 2025-09-10 |  | In Progress | Medium | FALSE | 0 | 7
TASK0521 | Team Meeting | Henry Davis | IT | 2025-12-18 | 2025-12-24 |  | In Progress | Low | FALSE | 0 | 1
TASK0522 | Product Launch | Frank Wilson | Finance | 2025-01-01 | 2025-01-15 | 2025-01-18 | Completed | Critical | TRUE | 3 | 4
TASK0523 | Performance Review | Frank Wilson | Finance | 2025-01-21 | 2025-02-19 | 2025-02-21 | Completed | High | TRUE | 2 | 9
TASK0524 | Product Launch | Carol White | IT | 2025-04-20 | 2025-05-06 | 2025-05-05 | Completed | High | FALSE | 0 | 6
TASK0525 | Vendor Evaluation | James Anderson | Sales | 2026-03-23 | 2026-03-26 | 2026-03-26 | Completed | Low | FALSE | 0 | 6
TASK0526 | Contract Negotiation | David Lee | Operations | 2025-10-04 | 2025-10-25 | 2025-10-24 | Completed | Medium | FALSE | 0 | 9
TASK0527 | Performance Review | Liam Jackson | HR | 2025-08-03 | 2025-08-07 |  | In Progress | Medium | FALSE | 0 | 4
TASK0528 | Performance Review | Karen Thomas | Finance | 2025-01-08 | 2025-01-28 |  | Cancelled | Medium | FALSE | 0 | 1
TASK0529 | Product Launch | Isabella Taylor | Operations | 2025-03-13 | 2025-04-01 |  | Overdue | Medium | TRUE | 5 | 4
TASK0530 | Code Review | Karen Thomas | Finance | 2025-06-21 | 2025-06-24 | 2025-06-24 | Completed | Low | FALSE | 0 | 2
TASK0531 | Quarterly Report | Maria Harris | IT | 2025-09-28 | 2025-10-13 | 2025-10-19 | Completed | Critical | TRUE | 6 | 4
TASK0532 | Process Improvement | Frank Wilson | Finance | 2026-01-20 | 2026-02-12 | 2026-02-16 | Completed | High | TRUE | 4 | 1
TASK0533 | Data Migration | Nathan Clark | Operations | 2025-11-26 | 2025-12-23 | 2025-12-25 | Completed | Medium | TRUE | 2 | 9
TASK0534 | Market Analysis | Bob Martinez | HR | 2025-07-16 | 2025-07-30 |  | Cancelled | Medium | FALSE | 0 | 6
TASK0535 | Risk Assessment | Maria Harris | IT | 2025-01-15 | 2025-01-20 |  | Overdue | Medium | TRUE | 3 | 7
TASK0536 | Budget Review | Grace Chen | HR | 2025-06-08 | 2025-06-19 |  | In Progress | High | FALSE | 0 | 7
TASK0537 | Dashboard Setup | Nathan Clark | Operations | 2025-02-08 | 2025-02-18 | 2025-02-17 | Completed | Low | FALSE | 0 | 4
TASK0538 | Policy Update | Henry Davis | IT | 2026-02-16 | 2026-03-15 |  | Overdue | High | TRUE | 7 | 6
TASK0539 | Code Review | Nathan Clark | Operations | 2026-02-10 | 2026-02-28 | 2026-02-27 | Completed | Low | FALSE | 0 | 6
TASK0540 | Data Migration | Grace Chen | HR | 2025-10-29 | 2025-11-07 | 2025-11-14 | Completed | Medium | TRUE | 7 | 1
TASK0541 | Contract Negotiation | Bob Martinez | HR | 2025-11-11 | 2025-11-28 |  | Overdue | Medium | TRUE | 4 | 6
TASK0542 | Policy Update | Grace Chen | HR | 2025-06-19 | 2025-06-27 | 2025-07-02 | Completed | Medium | TRUE | 5 | 3
TASK0543 | Stakeholder Report | Karen Thomas | Finance | 2025-04-30 | 2025-05-10 |  | In Progress | Medium | FALSE | 0 | 3
TASK0544 | Quarterly Report | Maria Harris | IT | 2025-10-27 | 2025-11-03 |  | Overdue | Medium | TRUE | 17 | 9
TASK0545 | Performance Review | Bob Martinez | HR | 2025-12-02 | 2025-12-06 |  | Overdue | Medium | TRUE | 9 | 10
TASK0546 | Product Launch | Nathan Clark | Operations | 2025-02-17 | 2025-03-12 |  | In Progress | High | FALSE | 0 | 10
TASK0547 | Performance Review | David Lee | Operations | 2025-09-12 | 2025-09-21 | 2025-09-20 | Completed | Low | FALSE | 0 | 10
TASK0548 | Budget Review | Henry Davis | IT | 2025-11-29 | 2025-12-17 |  | Overdue | Low | TRUE | 8 | 7
TASK0549 | Performance Review | Henry Davis | IT | 2025-08-13 | 2025-08-28 | 2025-08-29 | Completed | Medium | TRUE | 1 | 3
TASK0550 | Policy Update | Isabella Taylor | Operations | 2025-11-09 | 2025-12-02 | 2025-11-30 | Completed | Medium | FALSE | 0 | 8

## PivotData
Etiquetas de fila | Task Count | Etiquetas de fila | Task Count | Etiquetas de fila | Task Count
Finance | 91 | Cancelled | 60 | Critical | 53
HR | 140 | Completed | 308 | High | 147
IT | 116 | In Progress | 81 | Low | 118
Operations | 91 | Overdue | 101 | Medium | 232
Sales | 112 | Total general | 550 | Total general | 550
Total general | 550

## Dashboard
Task Completion Dashboard
Completion Rate |  | Overdue Tasks |  | Avg Days Overdue |  | On-Time Rate
| 0.56 |  | 0 |  | 5.7597 |  | 0
Esta forma representa una segmentación de datos. La segmentación de datos se admite en Excel 2010 y versiones posteriores. Si la forma se modificó en una versión anterior de Excel o si el libro se guardó en Excel 2003 o una versión anterior, no se puede usar la segmentación de datos.
Esta forma representa una segmentación de datos. La segmentación de datos se admite en Excel 2010 y versiones posteriores. Si la forma se modificó en una versión anterior de Excel o si el libro se guardó en Excel 2003 o una versión anterior, no se puede usar la segmentación de datos.
Esta forma representa una segmentación de datos. La segmentación de datos se admite en Excel 2010 y versiones posteriores. Si la forma se modificó en una versión anterior de Excel o si el libro se guardó en Excel 2003 o una versión anterior, no se puede usar la segmentación de datos.